## Section 2 - Identified Gaps
BNBR ApprovalMax Workflow Architecture - Section 2: Identified Gaps
# | Gap Details | Workflow Affected | Action Required | Response/Status / Responsibility
G1 | Board member ApprovalMax accounts not confirmed: Allan Oginga (Board Chairperson) and CPA Charles Muhia (Board Treasurer) do not appear on the staff payroll list. Their ApprovalMax email addresses, user accounts, and MFA setup are not documented. | All Tier 3 and Tier 4 workflows | Confirm email addresses and create ApprovalMax accounts for Allan Oginga and CPA Charles Muhia before go-live | Email for Charles Muhia is cmuhia@basicneedskenya.org. Update all references from Allan Oginga (Board Chairperson) to Boniface Chitayi (Board Chairperson) at chitayib@gmail.com.
G2 | IT Administrator not identified: The Data Access workflow refers to an IT Administrator for system access provisioning, but no individual is named or listed in the staff list. | Data Access Workflow (WF14) | Identify and document the IT Administrator responsible for access provisioning in ApprovalMax | Pending confirmation by the Operations & HR Manager or Executive Director.
G3 | Donor Report Financial Sign-Off workflow missing: Table 1 lists "Donor Report Financial Sign-Off" as Workflow #11 (Medium priority). No detailed procedure table was found in the source document. | Donor Report Workflow | Obtain and document the detailed steps for Donor Report Financial Sign-Off workflow | Signed sequentially by the Finance Manager, Programs Manager, and Executive Director.
G4 | Acting Finance Officer vs Acting Finance Manager title distinction: Janerose Nduta Motende is titled "Finance Assistant" on the January payroll but "Acting Finance Officer" in the Workflow Plan; Paul Ochieng' is "Finance Officer" on the January payroll but "Acting Finance Manager" in the Workflow Plan. The May 2026 staff list confirms revised titles. Confirm the operative titles for ApprovalMax user setup. | All workflows | Confirm operative titles for Janerose Nduta Motende and Paul Celvins Ochieng for ApprovalMax user configuration | Operative titles for Janerose Nduta Motende and Paul Celvins Ochieng are Acting Finance Officer and Acting Finance Manager, respectively.
G5 | Volunteer ApprovalMax access level: 35 volunteers are listed in the MERL Department. The source document does not specify what system access (if any) volunteers should have in ApprovalMax. | Data Access Workflow | Define and document volunteer access level in ApprovalMax (read-only/no access/limited requestor access) | Access level for the 35 volunteers listed in the MERL Department is set to limited requestor access.
G6 | Board ODC notification mechanism not specified: The Budget Adjustment workflow references "Board communication via ODC" but the specific communication channel (email, formal report, board meeting minute) is not defined. | Budget Adjustment Workflow (WF07) | Define the specific Board ODC notification mechanism and document in ApprovalMax as a notification action | Executed via BNBR Board ODC meetings; referenced by meeting invites and minutes.
G7 | Rosemary Gathara (Executive Director) status: The January 2026 payroll includes Rosemary Gathara as Executive Director. The May 2026 staff list and workflow document reference Rebecca Mbaya as Acting ED. Rosemary Gathara's departure or leave status is not documented in the workflow plan. | All ED-approval workflows | Confirm Rosemary Gathara's current employment status and whether her ApprovalMax account should be deactivated | Rosemary Gathara left the organization on May 15, 2026. Deactivate her ApprovalMax account.
G8 | Procurement prequalified supplier list: The workflow references that the Operations & HR Manager "maintains the prequalified supplier list" but the list itself and the process for adding/removing suppliers is not documented. | Purchase Requisition Workflow (WF01) | Provide the prequalified supplier list and document the supplier onboarding /offboarding process for ApprovalMax | Pending confirmation by the Operations & HR Manager.

## Section 3 - Policy Ambiguities
BNBR ApprovalMax Workflow Architecture - Section 3: Potential Policy Ambiguities
# | Ambiguity Description | Workflow Affected | Document Section | Recommendation | Response/Status / Responsibility
A1 | Bill approval at exactly KES 100,000: The bill approval table specifies "Acting Finance Manager approves bills KES 5,000 to 99,999" and "Acting ED approves bills above KES 100,000". The treatment of a bill for exactly KES 100,000 is ambiguous (is it 99,999 tier or 100,000+ tier?). | Supplier Bill Workflow (WF02) | Table 5 | Recommend confirming with Finance Manager: KES 100,000 treated as Tier 2 (requiring Acting ED approval) | We acknowledge the mix-up and therefore rely firmly on Policy Resolution: Section 4.2(b)(2) of the Finance Policy explicitly clears up this boundary condition: "Any disbursement above KES 100,000 must be approved by the executive director while anything above KES 500,000 requires approval of the board representative." Resolution Action: For values of exactly KES 100,000, the item remains under standard Finance Manager / Program Manager approval. Only amounts exceeding KES 100,000.00 automatically route up to the Executive Director (ED). Update ApprovalMax to reflect that KES 100,000 belongs to the lower threshold range.
A2 | Procurement splitting - 30-day rolling window: The procurement splitting control applies to "same supplier, same project code, within 30 days." It is not specified whether this is a rolling 30-day window or a calendar month. | Purchase Requisition (WF01) | Table 4 | Confirm with Operations & HR Manager whether this is a rolling 30-day window or a calendar month for ApprovalMax rule configuration | Section 3(a)(3.1.4) of the Procurement Policy dictates a strict ban on artificial division: "Procurement of goods or services may not be 'divided' artificially to lower the monetary value in order to evade the prescribed delegation levels..."Section 3(a)(3.1.4) of the Procurement Policy dictates a strict ban on artificial division: "Procurement of goods or services may not be 'divided' artificially to lower the monetary value in order to evade the prescribed delegation levels..." Resolution Action: While the policy document leaves out a specific day count (e.g., "30 days"), it establishes that any multiple orders placed with the same supplier for similar projects/services must be legally substantiated by the operations department and approved by a Procurement Committee. Recommendation: Configure ApprovalMax using a rolling 30-day window rule to flag transactions from the same vendor/project code to catch intentional structural workarounds.
A3 | Acting ED payroll self-segregation: The document states "Acting ED may not approve payroll entries she herself prepared in a Finance capacity; such entries are re-routed to Board Treasurer." It is not specified who monitors or flags this conflict automatically. | Payroll Workflow (WF05) | Table 9, Step 4 | Determine whether this is a manual declaration or an automated ApprovalMax routing rule. Document the trigger mechanism | Finance Policy on Control Activities 2.2.3(a) mandates absolute segregation of duties across authorization, execution, recording, and reconciliation. Because self-approval violates basic internal controls, this cannot rely on manual declarations.Recommendation: Setup an automated conditional routing rule in ApprovalMax: If Requester/Preparer = Acting ED, skip the ED Approval node and route directly to the Board Treasurer.
A4 | Disposal approval basis (original price vs. NBV): The disposal approval Tiers are based on original purchase price. However, for heavily depreciated assets, the original price may create disproportionate Board involvement. This is the stated policy - flagged for awareness only, not a gap. | Asset Disposal (WF10) | Table 14, Step 4 | Confirmed as explicit policy. No change required. Board to note this may require Board involvement for old low-value assets | Policy Resolution: Section 9(c)(v) of the Procurement Policy explicitly confirms this structure: " Disposal approvals shall be aligned to the procurement approval matrix based on the purchase price provided in section 8.1 of this policy."Recommendation / Resolution Action: No workflow change is required since this is an intended policy choice.
A5 | Single-sourcing at exactly KES 5,000: Single sourcing is "restricted to KES 5,000 or below." It is not clear if exactly KES 5,000 is permitted as single-source. | Purchase Requisition (WF01) | Table 4 | Recommend treating KES 5,000 as the maximum inclusive of single sourcing. Confirm with Operations & HR Manager | There is a slight contradiction between the text and the threshold matrix in the Procurement Policy, which must be hardcoded cleanly: Section 7: States single sourcing "shall be restricted to KES 5,000 or if more than KES 5,000 to specific conditions..." Section 8(a) Matrix: Lists single-sourcing from KES 0.00 to KES 4,999, and requires a minimum of 3 quotations starting precisely from KES 5,000 up to KES 99,999. Resolution Action: To follow the more conservative protocol established in the Section 8(a) threshold matrix, treat exactly KES 5,000 as the entry threshold requiring competitive bidding. Recommendation: Configure the automated workflow rule so that single-source configurations apply strictly up to KES 4,999.99, forcing a 3-quotation attachment validation at KES 5,000.00 and above.